## Sheet1
Task | Tanggal Mulai | Target Selesai | Tanggal Selesai | Nama Developer | Status
Preprocessing Data | 2021-10-15 | 2021-10-21 |  | Raffi | Waiting
Cleansing Data | 2021-10-22 | 2021-10-28 |  | Hanif | Waiting
Modelling Data | 2021-10-29 | 2021-10-06 |  | Raffi | Waiting
Augmentasi Data | 2021-11-07 | 2021-10-13 |  | Hanif | Waiting
Normalisasi Data | 2021-11-14 | 2021-10-20 |  | Raffi | Waiting
Fontend Web | 2021-11-21 | 2021-10-27 |  | Hanif | Waiting
Backend Web | 2021-11-28 | 2-Des-2021 |  | Raffi | Waiting
Config Flask | 3-Des-2021 | 10-Des-2021 |  | Hanif | Waiting